## Project Details
PROJECT OVERVIEW AND EVERY TEAM MEMBER'S
Project Name: Project Gift Basket
Team Name: Team Majesty
Team Member | Work in Project
K Abhiram | Development, Designing, Maintainance, Daily Report, JS Integration, Hosting, Automation Testing(LMS)
Tushar Prabhakar | Manual Testing(Project), Planning, Automation Testing(LMS)
Rohit Kumar Ray | Manual Testing(Project)
Sharsti Arya | Manual Testing(Project), Automation Testing(LMS)
Ayush Verma | Manual Testing(Project), Automation Testing(LMS)
T Saishree | Manual Testing(Project), Automation Testing(LMS)

## Today's Status
Date | Team Member Name | Work Done
01/04/2022 | K Abhiram | Developing some modules of Application
01/04/2022 | Tushar Prabhakar | Cross Browser Testing on Java module
01/04/2022 | Rohit Kumar Ray | Test cases for some modules in web application
01/04/2022 | Sharsti Arya | Test cases for some modules in web application
01/04/2022 | Ayush Verma | Test cases for some modules in web application
01/04/2022 | T Saishree | Cross Browser Testing on Assessment, Batch Calendar module

## Status of the Project
Project Name: Project Gift Basket
Project Module | Team Member Name | Expected Date | Completed Date | Status
Objectives of the Project | Tushar Prabhakar | 22/02/2022 | 22/02/2022 | Completed
| K Abhiram | 22/02/2022 | 22/02/2022 | Completed
SRS Document | K Abhiram | 22/02/2022 | 23/02/2022 | Completed
Test Plan Document | Sharsti Arya | 28/02/2022 | 28/02/2022 | Completed
| T Saishree | 28/02/2022 | 28/02/2022 | Completed
Project Presentation | K Abhiram | 04/04/2022 | 03/04/2022 | Completed
Test Scenarios | Tushar Prabhakar | 14/03/2022 | 14/03/2022 | Completed
Test Case Document - Login Module | Tushar Prabhakar | 06/03/2022 | 06/03/2022 | Completed
| Ayush Verma | 06/03/2022 | 06/03/2022 | Completed
Test Case Document - Product Catalogues Module
Test Case Document - Team Majesty Intro Module
Test Case Document - Project About Module
Test Case Document - Product Descriptions Module
Test Case Document - Home page Module
Test Case Document - Feedback Module
Test Case Document - Transaction Pages Module | Rohit Kumar Ray
Updated SRS Document | Tushar Prabhakar | 31/03/2022 | 01/04/2022 | Completed
Updated Test Plan Document | Sharsti Arya

## Daily Report
Date | Work Done
| K Abhiram | Tushar Prabhakar | Rohit Kumar Ray | Sharsti Arya | Ayush Verma | T Saishree
Till 29/03/2022 | Developed 85% modules of the Application, SRS Document preperation | Written Test Cases for 80% modules of the Application, Objective Planning | Working on the Database creation and connection | Written Test Cases for 80% modules of the Application, Test Plan preperation | Written Test Cases for 80% modules of the Application | Written Test Cases for 80% modules of the Application, Test Plan preperation
29/03/2022 | Developed Home page of the Application | Written Test Cases for some modules of the Application | Working on the Database creation and connection | Working on the Page Object Model of HCL LMS | Working on the Page Object Model of HCL LMS | Working on the Page Object Model of HCL LMS
30/03/2022 | Cross Browser Testing on Testing module, Feedback | Cross Browser Testing on Java module | Database, Tables created and working on connection to application | Cross Browser Testing on DQ, Score Card module | Cross Browser Testing on Workbook Calendar, WOD module | Cross Browser Testing on Assessment, Batch Calendar module
31/03/2022 | Developing some modules of Application, Cross Browser Testing on Invalid login and feedback | Tested on some modules of the project application, SRS Document updation | Working on database connection to application | Cross Browser Testing on DQ, Score Card, Valid Login module | Cross Browser Testing on Workbook Calendar, WOD module | Cross Browser Testing on Assessment, Batch Calendar module
01/04/2022 | Developing some modules of Application, Cross Browser Testing on Testing, Feedback | Cross Browser Testing on Java module, SRS Document updation | Test cases for some modules in web application | Test cases for some modules in web application | Test cases for some modules in web application | Cross Browser Testing on Assessment, Batch Calendar module